## Slide 1: Project Hawkeye 1 & 2
Project Kick-off Meeting (HE1 & HE2)
1st Sept 2025

## Slide 2: Agenda
Project Team Structure
HE1 Milestones and Deliverables
HE2 Milestones and Deliverables
Project Management Plan
Urgent / Critical Tasks

## Slide 3: Project Team Structure
David Siow
[Project Director]
Liow Sin Hwa
[Consultant]
CJ Lim
[Project Manager]
Eric See [Technical Lead]
Tan Jun Rong [Lead Developer]
Rafiq
[Lead UI Designer]
Liao Peiru [Business Analyst]
Dr Liu Jin [Lead Data Scientist]
Judy [Data Scientist]

## Slide 4: HE1 Project Milestones and Deliverables [1/3]
S/N | Milestones | Deliverables | Target Date
1 | Critical Design Review (CDR) | Project Management Plan (PMP) Preliminary System & Software Design UX/UI Design Process Work flow | August 2025
2 | Software Verification & Iteration #1 | Software Requirement Specification (Preliminary version) System Design Document (Preliminary version) | October 2025
3 | Software Verification & Iteration #2 | Software Requirement Specification (SRS) System Design Document | Jan 2026

## Slide 5: HE1 Project Milestones and Deliverables [2/3]
4 | Delivery of DBMS and Acceptance | Delivery of DBMS Deliver the Test Plan, Test Results and successfully conducted the following Acceptance Tests: Installation Test; System Functional Test; System Interface/Integration Test; System Performance Test; System Load Test Stress Test Source Code Security Test using SAST Tool User Acceptance Test Conduct Pre-UAT Training; Hardware/Software Configuration Document System Administration/Operations Document User Guide | October 2026

## Slide 6: HE1 Project Milestones and Deliverables [3/3]
5 | Commissioning Date & Completion of Training | Conduct in-house training with users: User Training using DBMS; User Training for Trainers; System Installation & Configuration Training; Training Proposal & Plan Training materials | November 2026
6 | Acceptance & Sign-off | Hardware Maintenance Plan Software & Application Maintenance Plan Source Code | March 2027
7 | End Warranty |  | Feb 2028

## Slide 7: HE2 Project Milestones and Deliverables [1/3]
S/N | Milestones | Deliverables | Target Date
1 | Preliminary Design Review (PDR) | Project Management Plan (PMP) | August 2025
2 | Critical Design Review (CDR) | Preliminary System & Software Design UX/UI Design Process Work flow | January 2026
3 | Software Verification & Iteration #1 | Software Requirement Specification (Preliminary version) System Design Document (Preliminary version) | April 2026
4 | Software Verification & Iteration #2 | Software Requirement Specification (SRS) System Design Document | July 2026

## Slide 8: HE2 Project Milestones and Deliverables [2/3]
5 | Delivery & Acceptance of Link Analysis Software to STE for Integration | Delivery of Link Analysis Deliver the Test Plan, Test Results and successfully conducted the following Acceptance Tests: Installation Test; System Functional Test; System Interface/Integration Test; System Performance Test; System Load Test Stress Test Source Code Security Test using SAST Tool User Acceptance Test Hardware/Software Configuration Document System Administration/Operations Document | April 2027

## Slide 9: HE2 Project Milestones and Deliverables [3/3]
6 | Delivery & Acceptance of Link Analysis Software | Conduct Pre-UAT training; User Guide | August 2027
7 | Commissioning Date & Completion of Training | Conduct in-house training with users: User Training using Link Analysis; User Training for Trainers; System Installation & Configuration Training; Training Proposal & Plan Training materials | September 2027
8 | Acceptance & Sign-off | Hardware Maintenance Plan Software & Application Maintenance Plan Source Code | January 2028
9 | End Warranty |  | January 2029

## Slide 10: What’s in Project Management Plan?
Quality Management Plan
  Coding Standard Guidelines
Risk Management Plan
Change Management Plan
Problem Management Plan
Configuration Management Plan
Communication Management Plan
Project Closure/Exit Management Plan

## Slide 11: Urgent/Critical Tasks
17th September 2025 – Data mapping workshop with End User
  Peiru, Dr. Liu – Lead the workshop session
October 2025 – Software V&I 1 [15%]
  Complete at least 75 – 80% of the UI design
  Refer to the documents, minutes and slides for workflow and designs
  Rafiq – Lead the UI design
  Eric and Jun Rong – Assist to prototype the UI and workflow
Agile Development Plan (by 15 September)
  Use the User Story to plan the sprint and align with the project milestones;
  Come out the Data Design***
  Eric – Lead the development team
Notes: Check with Peiru ..if she is comfortable to lead the workshop session

## Slide 12: UI design to be completed by 1st V&I (red box)

## Slide 13: Building a Cohesive Team
Notes: Talk a bit on the customer reaction with us and a good start for the team till now…
Not a very big team … but we can do it with commitments…
I understand most of us are not full-time working… but I believe that we are a professional individuals should

## Slide 14
Notes: Trust is a foundation for a cohesive team.
Constructive conflict… in debates.. Different in perspectives, explore solutions , strengthens bonds
Commitment… - on common goals
Accountability – high performing team stay accountable to one another… address unmet commitments…
Achieving Results … satisfaction…

## Slide 15: Thank you!